## Slide 1: A tale of two proposals, what went right, what went wrong
Richard Sanders Senior Scientist
SINTEF ICT, Norway

## Slide 2: From Idea to Project: Story 1 The Story of MIDAS

## Slide 3: MIDAS: The path to a submitted proposal
SINTEF Initiative
Capgemini “Digital Olympics” Initiative
IST Conference Den Haag Nov 2004 30 second presentation
1
Information Day Brussels Jan 2005 2 slides
2
Capgemini meeting Utrecht Feb 2005 Detailed discussions
3
Consortium meeting Warsaw Feb 2005 Start writing
4
MIDAS Proposal Submitted March 2005
5

## Slide 4: IST Conference, November 2004
Idea - Vague: “Mobility, wireless systems, data replication”
Consortium - Almost empty: SINTEF, maybe University of Oslo
IST Strategic Objective – Undecided: Try for “Mobile systems beyond 3G”; if that doesn’t work, try “ICT for Environmental Risk Management” in call 5
Application Area - Clear (though limited):
  Support for emergency staff responding to major accident
MIDAS advice:
Try to crystallize core technical idea at an early stage
Define partner roles, even though you don’t know their names yet
Decide on one strategic objective in the workprogramme, and go for it
1

## Slide 5: Information Day, January 2005
Idea - Still not clear enough
Consortium – No progress (though some roles defined)
Application area – Starting to have doubts: is it too limited?
Idea - Starting to emerge
Project description – Able to present 2 slides in 90 seconds, get idea across and contact numerous potential partners
MIDAS advice:
2
Produce a concise 3-4 page summary of your project as early as possible, to help you:
  Clarify your own ideas
  Communicate project concept to potential partners and National Contact Points (NCPs)
  Write a”Project Abstract” – and give all readers a positive impression of the project

## Slide 6: Capgemini meeting, February 2005
Idea - Full chaos when attempt integration with sports applications and new partner interests
Application area – Now convinced that mobile sports applications should be added to extend scope and applicability
Consortium - Good impression of three potential partners; high-quality and relevant:
  Capgemini: Major system integrator
  Appear Networks: Dynamic SME specialising in mobile platforms
  51pegasi: SME specialising in mobile applications for sports
MIDAS advice:
3
As you add new partners:
  Adopt some of their ideas; reject others
  Listen to all of them!

## Slide 7: After Capgemini meeting (1): Reducing Emphasis on Application Development
MIDAS advice:
Always consult officials
  Earlier: Commission officials
  Now: National Contact Points (NCPs)
... I can remind you perhaps, that proposals ... must address generic networking issues and provide innovative new solutions to significant problems, even when exemplified by a sporting or emergency context. The application itself should not be the centre of gravity of the proposal.
Best regards
Andy Houghton
IST Brussels
Extract from email from Commission Project Officer:

## Slide 8: After Capgemini meeting (2)
Aspects of ”balance”:
  SMEs
  ”Big names”: organisations the evaluators will recognise
MIDAS advice:
Make sure that partners have ”real” roles – and significant effort allocation
Apply the ”delete a partner” rule of thumb
  If deleting partner X will not obviously jeopordise the consortium, is X really needed?
Individual partner descriptions must answer 4 key questions:
  Type of organisation
  Specific skills/techologies brought to the project
  Role in the project
  Interest in project results

## Slide 9: Warsaw meeting, February 2005
Idea - Still struggling to crystallize – though we know what activities and research we want to carry out
Application area – Settled on mobile sports applications and emergencies – but match with technical idea is unclear
Consortium - Balance starting to look good (though still some holes)
MIDAS advice:
4
Unless key partners know each other well from previous co-operation: at least one meeting is essential to synchronise ideas

## Slide 10: After Warsaw meeting
Consortium - Telefonica added as ”Leading European mobile operator” and RATP as end-user for mobile emergency crew application
Idea - Develop a platform that makes it commercially feasible for the wider IT industry (not just telecom companies) to develop distributed mobile applications, especially where there is a very large number of users, the service has to be set up at short notice or for a limited time period, and the availability of infrastructure is limited
Applications – Now clearly fit ”idea”; each addresses some common issues and some unique ones

## Slide 11: Proposal Submitted 22nd March Evaluation results expected 14th June
5

## Slide 12: And the story has a happy ending...
Evaluation results June 2005:
  Positive remarks from evaluators; only a few minor negative ones
  Scored 28 points out of 30. Few proposals manage this
Contract negotiations started August 2005
Project started January 2006

## Slide 13: Paths that did not lead anywhere
Phone conferences with approx. 8 other research institutes/universities.
IP or STREP?
IP on “Semantic-based knowledge and content systems”
SINTEF Initiative
Capgemini “Digital Olympics” Initiative
Other Initiatives
IST Conference Den Haag Nov 2004 30 second presentation
1
Information Day Brussels Jan 2005 2 slides
2
Capgemini meeting Utrecht Feb 2005 Detailed discussions
3
Consortium meeting Warsaw Feb 2005 Start writing
4
MIDAS Proposal Submitted March 2005
5

## Slide 14: Story 2: Pluto’s downfall: What went wrong with an EU proposal

## Slide 15: Process: Linking consortium partners with core technical idea
Core technical idea
Partners
Unclear idea, going several places at once
Partner roles not all directed towards common goal

## Slide 16: Process: Linking application area with idea
Core technical idea
Application Area
Application area does not fully match proposal direction Mis-match between concrete application and academic concept

## Slide 17: Process: Linking partner with application
Core technical idea
Partners
Application Area
new partner
New partner matches application – but not other partners
Overall situation: proposal axes not synchronized

## Slide 18: Process: timing, “normal”
Cummulative effort
Time
Text 40-60% complete
Internal evaluation
Deadline
Approx. 3 weeks

## Slide 19: Process: timing, PLUTO
Cummulative effort
Time
Text 2% complete
Internal evaluation
Deadline
Approx. 3 weeks

## Slide 20: Content: Clarity
“Reading this makes me give up the will to live”
(said by one of the co-authors of PLUTO during a phone conference)

## Slide 21: Reasons for lack of clarity
Problems with overall quality of writing / structuring
Failure to separate:
  Input to project from partners' products & research
  Input to project from other projects
  What work will be done in the project
  Objectives
  Concrete results
  Impact: What becomes possible after the project

## Slide 22: Types of Success & Failure
Score > ~12 but: undeserved (problems when running project)
Score > ~12 Good proposal + project
Score 10-12
Score < 10 3 or more for each criterion
Score < 10 Under 3 for some criteria
FUNDED
NOT FUNDED
Success!!
“Harmless” Failure
Long-term damage to reputation by:
Harmful “success”
Peers (evaluators)
Partners
NCP
Score > ~12 But not funded anyway

## Slide 23: PLUTO: Signs of Failure
Score less than 10
Score less than 3 for criterion 1, criterion 3 (the ones most related to project concept)
Reviewer comments show:
  Not able to see any clear concept
  View proposal as “increment” on earlier work (because at least they can understand that...)
  Criticisms on details: “When evaluators feel unhappy with the clarity of the overall concept, it tends to annoy them and they find other things to complain about too.”

## Slide 24: PLUTO: final error – failing to learn
“New call ... offers a great chance for PLUTO....”
“We can probably keep the focus in a new proposal”
“I think the reviewers were just looking for buzzwords”
“How do the reviewers know better than us how....”

## Slide 25: From idea to proposal: axes
Project Idea
Project Proposal
Core scientific/technical idea
Consortium
Application area
Vague
Clear
Incomplete/ unbalanced
Complete/ balanced
Too vague or too specific/ dominant
Drives technological development and enables exploitation
Budget
IPR/ business aspects
Maybe know approx. total
Takes account of all partner rates
and wishes
Assume it will be OK
Potential conflicts
addressed

## Slide 26: Final Thoughts
Proceed with all technical and non-technical issues in parallel
Read and review: not just write
Nothing great is done without enthusiasm!